## Sheet1
PHASE 1: Set Up the API (15 minutes) | Step 1: Install Node.js (if not already installed) | Step 1: Run SQL script in SSMS ............... [⏸️ Not done yet]
| Step 2: Install API Dependencies | Step 2: Run npm install in PowerShell ........ [⏸️ Waiting for Step 1]
| Step 3: Create Database Read-Only User | Step 3: Create .env file ..................... [⏸️ Waiting]
| Step 4: Configure Database Connection | Step 4: Start API server ..................... [⏸️ Waiting]
| Step 5: Test the API Locally | Step 5: Test API ............................. [⏸️ Waiting]
Step 6: Test with Real Data
PHASE 2: Update Your Website (10 minutes)
PHASE 3: Deploy to Production (Choose One)

## Sheet2
PROJECT-K PHASES & STATUS
PHASE 1: DATABASE SETUP ⏳ IN PROGRESS
Task ID | Task | Status | Duration | Owner
1.1 | Analyze database structure (5 tables) | ✅ DONE | 1 hr | Completed
1.2 | Map table relationships & keys | ✅ DONE | 30 min | Completed
1.3 | Create SQL read-only user script | ✅ DONE | 15 min | Completed
1.4 | Execute SQL script in SSMS | 🟡 IN PROGRESS | 5 min | YOU ARE HERE
1.5 | Verify user permissions | ⏸️ PENDING | 5 min | Next
1.6 | Test database connection | ⏸️ PENDING | 5 min | Next
PHASE 2: API DEVELOPMENT ✅ 90% COMPLETE
2.1 | Design API architecture | ✅ DONE | 30 min | Completed
2.2 | Create Node.js API server code | ✅ DONE | 1 hr | Completed
2.3 | Implement SQL Server connection | ✅ DONE | 30 min | Completed
2.4 | Build database query logic (5-table join) | ✅ DONE | 45 min | Completed
2.5 | Add security features (rate limiting, validation) | ✅ DONE | 30 min | Completed
2.6 | Create environment configuration | ✅ DONE | 15 min | Completed
2.7 | Install Node.js dependencies | ✅ DONE | 2 min | Completed
2.8 | Configure .env file with credentials | 🟡 IN PROGRESS | 5 min | Waiting on 1.4
2.9 | Test API locally | ⏸️ PENDING | 15 min | Next
2.1 | Fix any bugs/issues | ⏸️ PENDING | 30 min | Next
PHASE 3: FRONTEND INTEGRATION ⏸️ NOT STARTED
3.1 | Update script.js to call live API | ⏸️ PENDING | 30 min | Waiting
3.2 | Replace hardcoded sample data | ⏸️ PENDING | 15 min | Waiting
3.3 | Add loading spinner/states | ⏸️ PENDING | 15 min | Waiting
3.4 | Handle "no tracking number" scenarios | ⏸️ PENDING | 15 min | Waiting
3.5 | Add error handling (PO not found, wrong zip) | ⏸️ PENDING | 15 min | Waiting
3.6 | Test frontend with real API | ⏸️ PENDING | 30 min | Waiting
PHASE 4: DEPLOYMENT ⏸️ NOT STARTED
4.1 | Choose hosting platform (Railway/Company Server) | ⏸️ PENDING | 15 min | Decision needed
4.2 | Set up hosting account | ⏸️ PENDING | 10 min | Waiting
4.3 | Push code to GitHub | ⏸️ PENDING | 10 min | Waiting
4.4 | Deploy API to production | ⏸️ PENDING | 20 min | Waiting
4.5 | Configure production environment variables | ⏸️ PENDING | 10 min | Waiting
4.6 | Set up database firewall rules | ⏸️ PENDING | 15 min | IT/DBA
4.7 | Update frontend to use production API URL | ⏸️ PENDING | 5 min | Waiting
4.8 | Deploy website to production | ⏸️ PENDING | 15 min | Waiting
PHASE 5: TESTING & GO-LIVE ⏸️ NOT STARTED
5.1 | Test with real customer PO numbers | ⏸️ PENDING | 30 min | Waiting
5.2 | Test error scenarios (invalid PO, wrong zip) | ⏸️ PENDING | 15 min | Waiting
5.3 | Test orders with tracking numbers | ⏸️ PENDING | 15 min | Waiting
5.4 | Test orders without tracking numbers | ⏸️ PENDING | 15 min | Waiting
5.5 | Performance testing (load test) | ⏸️ PENDING | 30 min | Waiting
5.6 | Security audit | ⏸️ PENDING | 30 min | Waiting
5.7 | UAT with internal users | ⏸️ PENDING | 1 day | Waiting
5.8 | Fix any issues found in testing | ⏸️ PENDING | Variable | Waiting
5.9 | GO LIVE! 🚀 | ⏸️ PENDING | - | Target